## Sheet1
Setup Database Backend |  | Build generating Ais |  | Generate Dataset 1 | [5 empty] | Test and Refactor
Start Day | 1 | Start Day | 12 | Start Day | 20 |  |  |  |  | Start Day | 47
Finish Day: | 11 | Finish Day: | 19 | Finish Day: | 25 |  |  |  |  | Finish Day: | 52
Duration | 10 | Duration | 7 | Duration | 5 | Debug and Integrate |  | Learning Process |  | Duration | 5 | Final Testing |  | Create Presentation
[6 empty] | Start Day | 26 | Start Day | 41 |  |  | Start Day | 55 | Start Day | 63
[6 empty] | Finish Day: | 40 | Finish Day: | 46 |  |  | Finish Day: | 62 | Finish Day: | 65
Understand Genetic AI |  | Draft Genetic AI |  |  |  | Duration | 14 | Duration | 5 | Integration with UX |  | Duration | 7 | Duration | 2
Start Day | 1 | Start Day | 6 | [6 empty] | Start Day | 47
Finish Day: | 5 | Finish Day: | 20 | [6 empty] | Finish Day: | 54
Duration | 4 | Duration | 14 | [6 empty] | Duration | 7
[6 empty] | Build Mobile Front End |  | Build Mobile Backend
[6 empty] | Start Day | 30 | Start Day | 38
[6 empty] | Finish Day: | 37 | Finish Day: | 45
[6 empty] | Duration | 7 | Duration | 7
Days til Completion:
65
Days into Project:
0
Gantt Chart
Task | Start Day | Duration | Task Duration
Setup Database Backend | 1 | 10 | 11
Understand Genetic AI | 1 | 4 | 5
Draft Genetic AI | 6 | 14 | 20
Build generating Ais | 12 | 7 | 19
Generate Dataset 1 | 20 | 5 | 25
Debug and Integrate | 26 | 14 | 40
Build Mobile Front End | 30 | 7 | 37
Build Mobile Backend | 38 | 7 | 45
Learning Process | 41 | 46 | 5
Test and Refactor | 47 | 5 | 52
Integration with UX | 47 | 7 | 54
Final Testing | 55 | 7 | 62
Create Presentation | 63 | 2 | 65